## 1. Product Overview
Item | Description
Product Name | CarCare
Product Vision/ Purpose | To create an intelligent, all-in-one car care ecosystem that simplifies vehicle maintenance through AI automation, real-time insights, and reliable service connectivity.
Business Goals / Key Success factors | Simplify and automate vehicle maintenance using AI.Reduce maintenance costs and extend vehicle lifespan. Connect car owners with trusted nearby service centers.AI Predictive Maintenance,Automated Service Scheduling,GPS-Based Garage Locator
Primary Stakeholders | AI-Based Vehicle Maintenance Management System include car owners, mechanics, car manufacturers, insurance companies, and fleet managers.

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | User Registration & Login | US1 | As a user, I want to create an account and log in securely. | Database for users, authentication API, password encryption | Must Have | 5 | In Progress | Dev Team | Verify registration and login validation | QA Team
E2 | Vehicle Profile Management | US2 | As a user, I want to add and manage details of my car. | CRUD operations, car database schema | Must Have | 3 | Completed | Dev Team | Test add, edit, delete car info | QA Team
E3 | AI Predictive Maintenance | US3 | As a user, I want to get alerts before service or failure occurs. | AI model integration, sensor data input, notification system | Should Have | 8 | In Progress | AI Engineer | Test prediction accuracy & alert trigger | QA Team
E4 | Service Scheduling | US4 | As a user, I want automatic reminders for upcoming maintenance. | Calendar integration, notification API | Must Have | 5 | In Progress | Dev Team | Test reminder generation & accuracy | QA Team
E5 | Nearby Garage Locator | US5 | As a user, I want to find nearby garages using GPS. | GPS API, map integration (Leaflet.js/OpenStreetMap) | Must Have | 5 | Completed | Dev Team | Verify map accuracy & location listing | QA Team
E6 | Expense Tracking | US6 | As a user, I want to record and view my service and repair costs. | Expense database, dashboard UI | Should Have | 4 | In Progress | Dev Team | Validate cost entry, update, and summary | QA Team
E7 | Emergency Assistance | US7 | As a user, I want quick access to emergency contacts nearby. | GPS-based search, SOS API integration | Could Have | 3 | Planned | Dev Team | Check SOS trigger and nearest help | QA Team
E8 | Review & Feedback System | US8 | As a user, I want to rate and review service centers. | Review database, rating API | Could Have | 2 | Planned | Dev Team | Test rating submission & display | QA Team

## 3. Roadmap
Release | Target Date | Key Features / List Epic Names | Dependencies | Demo Status
v0.1 | 2025-11-15 12:00 | User Registration, Secure Login, Dashboard MVP | Database setup, Authentication API | On Track
v0.2 | 2025-11-22 12:00 | Vehicle Profile Management, Basic Service Scheduling | CRUD operations, Notification API | Planned
v0.3 | 2025-11-29 12:00 | AI Predictive Maintenance, Smart Alerts | AI model integration, Data preprocessing module | Planned
v0.4 | 2025-12-06 12:00 | GPS-based Garage Locator, Map Integration | Leaflet.js / OpenStreetMap API, Location services | Planned
v0.5 | 2025-12-13 12:00 | Expense Tracking Dashboard, Report Generation | Data visualization library, Local DB setup | Yet to Plan
v1.0 | 2025-12-20 12:00 | Public Launch – All Core Features, Customer & Mechanic Portal | Complete system integration, Backend optimization | Yet to Plan
v1.1 | 2025-12-27 12:00 | Emergency Assistance, Feedback System, Premium Features | GPS module, Review database, API enhancements | Yet to Plan

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner